## Handoff testing
Test pass x | Total test cases | Excution test cases count | Required QFE bugs Number | Validated QFE bugs Number | Test pass time(day) | Total executed Features
TP1 | 1958 | 1958 |  |  | 199 | 33
TP2 | 1966 | 1461 |  |  | 99 | 28
TP3 | 1966 | 1520 |  |  | 85 | 30
TP4 | 1944 | 1498 |  |  | 81.5 | 30
TP5 | 1924 | 1478 |  |  | 76.5 | 30
TP6 | 1922 | 1476 |  |  | 75 | 30
TP7 | 1878 | 1392 |  |  | 70 | 30
TP8 | 1803 | 1422 |  |  | 79 | 33
April PU | 1816 | 747 |  |  | 59 | 31
TP9 | 1809 | 632 |  |  | 36.5 | 24
May PU | 1828 | 694 | 1 | 1 | 55.5 | 30
TP10 | 1828 | 1447 |  |  | 73.5 | 36
June PU | 1828 | 749 | 0 | 0 | 47.5 | 32
TP11 | 1834 | 1453 |  |  | 65 | 36
July PU | 1834 | 755 | 1 | 1 | 51.5 | 32
TP12 | 1282 | 901 |  |  | 60 | 36
August PU | 1324 | 1116 | 3 | 3 | 48 | 32
TP13 | 1324 | 943 |  |  | 58 | 36
September PU | 1340 | 777 | 0 | 0 | 53.5 | 33
TP14 | 1334 | 927 |  |  | 55 | 36
October PU | 1334 | 780 | 1 | 1 | 48 | 34
TP15 | 1336 | 929 |  |  | 57 | 36
November PU | 1332 | 778 | 2 | 2 | 65 | 34
TP16 | 1353 | 958 |  |  | 55 | 36
TP17 | 1353 | 713 |  |  | 37.5 | 17
December PU | 1375 | 852 | 0 | 0 | 50 | 37
TP18 | 1375 | 713 |  |  | 37 | 17

## New features testing
New features | Handoff date | Supplier resources ramp up a new feature testing task within x days | One Test pass time | Test pass | Comments
Custom Tiles | 2015-09-14 | 3 | 2 | 12
Hybrid Picker V1 | 2016-01-12 | 6 | 4 | 6
Hybrid Picker V2 | 2016-07-12 | 4 | 3 | 20
SP insights | 2016-08-24 | 3 | 3 | 11
Taxonomy | 2016-03-22 | 5 | 4 | 8
Follow Sites Hot Fix | 2016-05-11 | 4 | 2 | 5
Hybrid App Launcher for 2013 | 2016-05-30 | 5 | 5 | 7
Hybrid Property Import | 2016-02-06 | 2 | 3 | 2
Accessibility | 2016-05-31 | 5 | 5 | 3
RBS | 2016-08-08 | 10 | 2 | 6
Note on B1: Author: FTE give this feature to our team.

## Bug
Bug ID | Area | Feature | Severity | Open date | Change date | Status | Resolution | Open by | Found from which work item | Test pass X | From test cases | From Ad-hoc | Valid or not | Bug validation time after build ready | Mis-opened bug | Miss bug from Test cases execution | Comments
[9 empty] | Test pass/Smoke/New features testing/Ad-hoc task |  | Default-Not from test case | Default-Not from Ad-hoc | Y/N-Default Invalid |  | Default-No
2307454 | SOX | Setup | 3 | 2015-06-01 | 2015-07-17 | Closed | By Design | v-dandl | Test pass | TP1 |  | Yes
2522848 | CASH | B2B | 2 | 2015-09-01 | 2015-09-15 | Closed | By Design | v-baoz | Test pass | TP1 | Yes
2314006 | SOX | Setup | 1 | 2015-06-03 | 2015-07-17 | Closed | By Design | v-dandl | Test pass | TP1 | Yes
2314239 | SOX | Setup | 3 | 2015-06-03 | 2015-07-17 | Closed | By Design | v-xiasha | Test pass | TP1 |  | Yes
2626896 | CASH | Setup | 3 | 2015-10-20 | 2015-10-22 | Closed | By Design | v-dandl | Test pass | TP2 | Yes
2639472 | CASH | Setup | 2 | 2015-10-26 | 2015-10-29 | Closed | By Design | v-xiasha | Test pass | TP2 | Yes
2361745 | SOX | Setup | 1 | 2015-06-18 | 2015-07-08 | Closed | Fixed | v-dandl | Test pass | TP1 |  | Yes | Valid
2348865 | SOX | Setup | 1 | 2015-06-12 | 2015-08-19 | Closed | Duplicate | v-dandl | Test pass | TP1 | Yes
2358059 | SOX | Setup | 1 | 2015-06-17 | 2015-08-18 | Closed | Duplicate | v-dandl | Test pass | TP1 | Yes
2627034 | SPEED | B2B |  | 2015-10-20 | 2015-11-04 | Closed | Fixed | v-baoz | Test pass | TP2 | Yes |  | Valid
2621764 | CASH | B2B |  | 2015-10-16 | 2015-10-26 | Closed | Not Repro | v-baoz | Test pass | TP2 | Yes
2914424 | SOX | Onprem | 2 | 2016-01-15 | 2016-10-26 | Closed | Fixed | v-baoz | Test pass | TP6 | Yes |  | Valid
3095876 | SOX | B2B | 3 | 2016-05-25 | 2016-11-18 | Closed | Not Repro | v-dandl | PU verify | June PU |  | Yes
3124905 | Onprem | B2B | 2 | 2016-06-22 | 2016-07-19 | Closed | By Design | v-dandl | PU verify | July PU | Yes
2658495 | SPEED | B2B |  | 2015-11-04 | 2015-12-02 | Closed | Won't Fix | v-baoz | Test pass | TP2 | Yes
2309783 | SOX | V2V | 3 | 2015-06-02 | 2015-07-17 | Closed | Not Repro | v-xiasha | Test pass | TP1 | Yes
2387138 | CASH | V2V | 2 | 2015-06-29 | 2015-07-17 | Closed | Not Repro | v-xiasha | Test pass | TP1 | Yes
2387139 | CASH | V2V | 2 | 2015-06-29 | 2015-07-17 | Closed | Not Repro | v-xiasha | Test pass | TP1 | Yes
2387143 | SOX | V2V | 3 | 2015-06-29 | 2015-07-17 | Closed | Not Repro | v-xiasha | Test pass | TP1 | Yes
2392699 | CASH | V2V | 2 | 2015-07-01 | 2015-08-17 | Closed | Not Repro | v-xiasha | Test pass | TP1 | Yes
2395495 | CASH | V2V | 2 | 2015-07-02 | 2015-08-28 | Closed | Not Repro | v-xiasha | Test pass | TP1 | Yes
2395590 | CASH | V2V | 1 | 2015-07-02 | 2015-08-17 | Closed | Not Repro | v-xiasha | Test pass | TP1 | Yes
2398636 | CASH | V2V | 2 | 2015-07-03 | 2015-08-17 | Closed | Not Repro | v-edyin | Test pass | TP1 | Yes
2398696 | CASH | V2V | 2 | 2015-07-03 | 2015-08-17 | Closed | Not Repro | v-edyin | Test pass | TP1 | Yes
2400619 | CASH | V2V | 2 | 2015-07-06 | 2015-08-17 | Closed | Not Repro | v-edyin | Test pass | TP1 | Yes
2400631 | CASH | V2V | 2 | 2015-07-06 | 2015-08-17 | Closed | Not Repro | v-edyin | Test pass | TP1 | Yes
2400638 | CASH | V2V | 2 | 2015-07-06 | 2015-08-17 | Closed | Not Repro | v-edyin | Test pass | TP1 | Yes
2403226 | CASH | V2V | 2 | 2015-07-07 | 2015-08-17 | Closed | Not Repro | v-edyin | Test pass | TP1 | Yes
2403243 | CASH | V2V | 2 | 2015-07-07 | 2015-08-17 | Closed | Not Repro | v-edyin | Test pass | TP1 | Yes
2406313 | CASH | V2V | 2 | 2015-07-08 | 2015-08-17 | Closed | Not Repro | v-edyin | Test pass | TP1 | Yes
2406320 | CASH | V2V | 1 | 2015-07-08 | 2015-08-17 | Closed | Not Repro | v-edyin | Test pass | TP1 | Yes
2436488 | Office Developer Platform | Sandbox | 2 | 2015-07-22 | 2015-10-27 | Closed | Fixed | v-dandl | Test pass | TP1 | Yes |  | Valid
2439151 | Office Developer Platform | Sandbox | 3 | 2015-07-23 | 2015-12-02 | Active |  | v-dandl | Test pass | TP1 | Yes |  | Valid
2439181 | Office Developer Platform | Sandbox | 3 | 2015-07-23 | 2015-12-02 | Active |  | v-dandl | Test pass | TP1 | Yes |  | Valid
2441908 | Office Developer Platform | Sandbox | 3 | 2015-07-24 | 2015-12-02 | Active |  | v-dandl | Test pass | TP1 | Yes |  | Valid
2442348 | Office Developer Platform | Sandbox | 3 | 2015-07-24 | 2015-12-02 | Closed | Fixed | v-dandl | Test pass | TP1 | Yes |  | Valid
2442358 | Office Developer Platform | Sandbox | 2 | 2015-07-24 | 2015-12-02 | Closed | Fixed | v-dandl | Test pass | TP1 | Yes |  | Valid
2442360 | Office Developer Platform | Sandbox | 3 | 2015-07-24 | 2015-12-02 | Active |  | v-dandl | Test pass | TP1 | Yes |  | Valid
2449051 | Office Developer Platform | Sandbox | 2 | 2015-07-27 | 2015-12-02 | Closed | Fixed | v-dandl | Test pass | TP1 | Yes |  | Valid
2449077 | Office Developer Platform | Sandbox | 3 | 2015-07-27 | 2015-12-02 | Closed | Fixed | v-dandl | Test pass | TP1 | Yes |  | Valid
2449086 | Office Developer Platform | Sandbox | 2 | 2015-07-27 | 2015-12-02 | Closed | Fixed | v-dandl | Test pass | TP1 | Yes |  | Valid
2449092 | Office Developer Platform | Sandbox |  | 2015-07-27 | 2015-12-02 | Closed | Fixed | v-dandl | Test pass | TP1 | Yes |  | Valid
2629602 | Storage, Networking and Performance | MinRole | 2 | 2015-10-21 | 2015-11-03 | Closed | By Design | v-liach | Test pass | TP2 | Yes
2649491 | CASH | MinRole |  | 2015-10-30 | 2015-11-03 | Closed | By Design | v-liach | Test pass | TP2 | Yes
2472111 | CASH | Quota | 2 | 2015-08-07 | 2015-08-17 | Closed | Duplicate | v-dandl | Test pass | TP1 | Yes
2472115 | CASH | Quota | 2 | 2015-08-07 | 2015-08-17 | Closed | Duplicate | v-dandl | Test pass | TP1 | Yes
2472123 | Storage, Networking and Performance | Quota | 3 | 2015-08-07 | 2015-08-17 | Closed | Duplicate | v-dandl | Test pass | TP1 | Yes
2472134 | CASH | Quota | 3 | 2015-08-07 | 2015-08-17 | Closed | Duplicate | v-dandl | Test pass | TP1 | Yes
2472136 | CASH | Quota | 2 | 2015-08-07 | 2015-08-17 | Closed | Duplicate | v-dandl | Test pass | TP1 | Yes
2472139 | CASH | Quota | 2 | 2015-08-07 | 2015-08-17 | Closed | Duplicate | v-dandl | Test pass | TP1 | Yes
2472141 | CASH | Quota | 2 | 2015-08-07 | 2015-08-17 | Closed | Duplicate | v-dandl | Test pass | TP1 | Yes
2472144 | CASH | Quota | 2 | 2015-08-07 | 2015-08-17 | Closed | Duplicate | v-dandl | Test pass | TP1 | Yes
2472119 | Office ecoSystem | Quota | 3 | 2015-08-07 | 2015-08-17 | Closed | Won't Fix | v-dandl | Test pass | TP1 | Yes
2472132 | CASH | Quota | 2 | 2015-08-07 | 2015-08-12 | Closed | Won't Fix | v-dandl | Test pass | TP1 | Yes
2472174 | CASH | FCW |  | 2015-08-07 | 2015-09-03 | Closed | By Design | v-liach | Test pass | TP1 | Yes
2475264 | SPPPLAT | Bug Bash |  | 2015-08-10 | 2015-08-28 | Closed | Won't Fix | v-xiasha | Bug Bash |  |  | Yes | Valid
2475265 | SOX | Bug Bash | 3 | 2015-08-10 | 2015-08-17 | Closed | By Design | v-liach | Bug Bash |  |  | Yes
2475332 | SOX | Bug Bash |  | 2015-08-10 | 2015-08-17 | Closed | By Design | v-xiasha | Bug Bash |  |  | Yes
2475413 | SPPPLAT | Bug Bash |  | 2015-08-10 | 2015-08-28 | Closed | Not Repro | v-yuxiaw | Bug Bash |  |  | Yes
2475431 | OCW | Bug Bash |  | 2015-08-10 | 2015-09-18 | Closed | By Design | v-liach | Bug Bash |  |  | Yes
2475432 | SPPPLAT | Bug Bash |  | 2015-08-10 | 2015-10-30 | Closed | Not Repro | v-yuxiaw | Bug Bash |  |  | Yes |  |  | Yes
2475450 | SOX | Bug Bash | 3 | 2015-08-10 | 2015-08-12 | Closed | By Design | v-dandl | Bug Bash |  |  | Yes
2475454 | SOX | Bug Bash |  | 2015-08-10 | 2015-08-17 | Closed | By Design | v-liach | Bug Bash |  |  | Yes
2475463 | SOX | Bug Bash |  | 2015-08-10 | 2015-08-17 | Closed | Won't Fix | v-pengwu | Bug Bash |  |  | Yes
2475467 | SOX | Bug Bash |  | 2015-08-10 | 2015-08-10 | Closed | By Design | v-bitang | Bug Bash |  |  | Yes
2475489 | Access | Bug Bash |  | 2015-08-10 | 2015-10-16 | Closed | Duplicate | v-liach | Bug Bash |  |  | Yes |  |  | Yes
2475504 | OCW | Bug Bash |  | 2015-08-10 | 2015-08-17 | Closed | By Design | v-bitang | Bug Bash |  |  | Yes
2475511 | SPPPLAT | Bug Bash |  | 2015-08-10 | 2015-09-18 | Closed | Won't Fix | v-liach | Bug Bash |  |  | Yes | Valid
2475524 | SPPPLAT | Bug Bash | 2 | 2015-08-10 | 2015-08-18 | Closed | By Design | v-dandl | Bug Bash |  |  | Yes
2475525 | SOX | Bug Bash |  | 2015-08-10 | 2015-08-17 | Closed | By Design | v-yuxiaw | Bug Bash |  |  | Yes
2475534 | Workplace Experiences | Bug Bash |  | 2015-08-10 | 2015-08-28 | Closed | Won't Fix | v-yuxiaw | Bug Bash |  |  | Yes | Valid
2475542 | SPPPLAT | Bug Bash | 3 | 2015-08-10 | 2015-08-18 | Closed | By Design | v-dandl | Bug Bash |  |  | Yes
2475554 | SOX | Bug Bash |  | 2015-08-10 | 2015-08-17 | Closed | By Design | v-pengwu | Bug Bash |  |  | Yes
2475566 | Experiences | Bug Bash |  | 2015-08-10 | 2015-12-01 | Active |  | v-yuxiaw | Bug Bash |  |  | Yes | Valid
2475631 | SPPPLAT | Bug Bash |  | 2015-08-10 | 2015-08-19 | Closed | Duplicate | v-bitang | Bug Bash |  |  | Yes |  |  | Yes
2472087 | CASH | MinRole | 3 | 2015-08-07 | 2015-09-07 | Closed | Duplicate | v-edyin | Test pass | TP1 | Yes
2478373 | Workplace Experiences | Bug Bash |  | 2015-08-11 | 2015-09-16 | Closed | Won't Fix | v-bitang | Bug Bash |  |  | Yes | Valid
2486052 | Office ecoSystem | PRIME |  | 2015-08-14 | 2015-08-18 | Closed | By Design | v-bitang | Test pass | TP1 |  | Yes
2486133 | MI6 | SCOM |  | 2015-08-14 | 2015-10-19 | Closed | Won't Fix | v-xiasha | Test pass | TP1 | Yes
2494964 | SOX | PRIME |  | 2015-08-19 | 2015-09-22 | Closed | By Design | v-bitang | Test pass | TP1 | Yes
2495006 | SOX | PRIME |  | 2015-08-19 | 2015-09-22 | Closed | By Design | v-bitang | Test pass | TP1 | Yes
2495059 | SOX | PRIME |  | 2015-08-19 | 2015-09-22 | Closed | By Design | v-bitang | Test pass | TP1 | Yes
2502305 | SOX | Prime |  | 2015-08-21 | 2015-09-14 | Closed | By Design | v-bitang | Test pass | TP1 | Yes
2514039 | SOX | PRIME |  | 2015-08-27 | 2015-09-24 | Closed | By Design | v-bitang | Test pass | TP1 | Yes
2692982 | SOX | Prime |  | 2015-11-23 | 2015-11-24 | Closed | By Design | v-bitang | Test pass | TP3 | Yes
2502090 | SOX | PRIME |  | 2015-08-21 | 2015-09-11 | Closed | Duplicate | v-bitang | Test pass | TP1 | Yes |  |  |  | Yes
2502400 | People and Org Platform | Stsadmin |  | 2015-08-21 | 2015-12-01 | Active |  | v-xiasha | Test pass | TP1 | Yes |  | Valid
2877309 | SOX | Backup & Restore | 3 | 2015-12-16 | 2015-12-17 | Closed | By Design | v-baoz | Test pass | TP5 | Yes
2511945 | SOX | Backup & Restore | 3 | 2015-08-26 | 2015-09-08 | Closed | Fixed | v-dandl | Test pass | TP1 | Yes |  | Valid
2897093 | CASH | Pre-install | 2 | 2016-01-04 | 2016-01-11 | Closed | Duplicate | v-xiasha | Test pass | TP6 |  | Yes
2511930 | SOX | Backup & Restore | 2 | 2015-08-26 | 2015-09-22 | Closed | Won't Fix | v-dandl | Test pass | TP1 | Yes
2511938 | SOX | Backup & Restore | 3 | 2015-08-26 | 2015-09-22 | Closed | Won't Fix | v-dandl | Test pass | TP1 | Yes
2514032 | CASH | Prime |  | 2015-08-27 | 2015-09-15 | Closed | Not Repro | v-bitang | Test pass | TP1 | Yes
2706179 | CASH | Prime | 2 | 2015-12-02 | 2015-12-03 | Closed | Won't Fix | v-dandl | Test pass | TP4 | Yes |  | Valid
2516421 | Office Developer Platform | Sandbox | 2 | 2015-08-28 | 2016-01-18 | Closed | Fixed | v-dandl | Test pass | TP2 | Yes |  | Valid
2516429 | Office Developer Platform | Sandbox | 2 | 2015-08-28 | 2016-01-18 | Closed | Fixed | v-dandl | Test pass | TP2 | Yes |  | Valid
2516433 | Office Developer Platform | Sandbox | 2 | 2015-08-28 | 2016-01-18 | Closed | Not Repro | v-dandl | Test pass | TP2 | Yes
2516440 | Office Developer Platform | Sandbox | 2 | 2015-08-28 | 2016-01-18 | Closed | Not Repro | v-dandl | Test pass | TP2 | Yes
2406331 | CASH | V2V | 2 | 2015-07-08 | 2015-08-17 | Closed | Not Repro | v-edyin | Test pass | TP1 | Yes
2544412 | Office Developer Platform | Sandbox | 2 | 2015-09-10 | 2015-09-15 | Closed | Fixed | v-dandl | Test pass | TP2 | Yes |  | Valid
2561156 | People and Org Platform | Stsadmin |  | 2015-09-18 | 2015-12-03 | Closed | Won't Fix | v-xiasha | Test pass | TP1 | Yes
2574516 | SPEED | Web Application | 3 | 2015-09-24 | 2015-09-25 | Closed | Fixed | v-xiuye | Test pass | TP1 | Yes |  | Valid
2574534 | SPEED | Web Application | 3 | 2015-09-24 | 2015-09-28 | Closed | Fixed | v-xiuye | Test pass | TP1 | Yes |  | Valid
2574601 | SPEED | Web Application |  | 2015-09-24 | 2015-10-12 | Closed | Won't Fix | v-xiuye | Test pass | TP1 | Yes
2580331 | Storage, Networking and Performance | Stsadmin |  | 2015-09-28 | 2015-11-04 | Closed | Won't Fix | v-xiasha | Test pass | TP1 | Yes |  | Valid
2580654 | Workplace Experiences | UPA | 2 | 2015-09-28 | 2015-12-01 | Active |  | v-qinglw | Test pass | TP1 | Yes |  | Valid
2580657 | Workplace Experiences | UPA | 2 | 2015-09-28 | 2015-12-01 | Active |  | v-qinglw | Test pass | TP1 | Yes |  | Valid
2582470 | People and Org Platform | UPA | 2 | 2015-09-29 | 2015-10-08 | Closed | Fixed | v-pengwu | Test pass | TP1 | Yes |  | Valid
2582516 | Workplace Experiences | UPA | 2 | 2015-09-29 | 2015-12-01 | Active |  | v-qinglw | Test pass | TP1 | Yes |  | Valid
2582754 | People and Org Platform | UPA | 2 | 2015-09-29 | 2015-11-26 | Closed | By Design | v-yzan | Test pass | TP1 | Yes
2608144 | Service Fabric Experience | IPU |  | 2015-10-09 | 2015-11-04 | Closed | Won't Fix | v-baoz | Test pass | TP1 | Yes |  | Valid
2614392 | SOX | Stsadmin | 2 | 2015-10-13 | 2015-10-19 | Closed | By Design | v-xiasha | Test pass | TP2 | Yes
2619229 | People and Org Platform | Mysite | 2 | 2015-10-15 | 2015-11-20 | Closed | Won't Fix | v-yiti | Test pass | TP2 | Yes
2621720 | People and Org Platform | UPA | 2 | 2015-10-16 | 2015-11-26 | Closed | Won't Fix | v-pengwu | Test pass | TP1 | Yes |  | Valid
2897101 | CASH | Pre-install | 2 | 2016-01-04 | 2016-01-11 | Closed | By Design | v-xiasha | Test pass | TP6 |  | Yes
2622084 | People and Org Platform | UPA | 2 | 2015-10-16 | 2015-10-20 | Closed | By Design | v-yancji | Test pass | TP1 | Yes
2629772 | SOX | Smoke | 3 | 2015-10-21 | 2015-10-22 | Closed | By Design | v-dandl | Smoke |  |  | Yes
2412145 | CASH | V2V | 2 | 2015-07-10 | 2015-08-17 | Closed | Not Repro | v-edyin | Test pass | TP1 | Yes
2893850 | CASH | Pre-install | 2 | 2015-12-30 | 2016-01-11 | Closed | Duplicate | v-xiasha | Test pass | TP5 | Yes
2472088 | CASH | MinRole | 2 | 2015-08-07 | 2015-10-08 | Closed | Duplicate | v-edyin | Test pass | TP1 | Yes
2632175 | Excel Israel | Smoke | 3 | 2015-10-22 | 2015-12-14 | Closed | Not Repro | v-dandl | Smoke |  |  | Yes
2632168 | OCW | Smoke | 3 | 2015-10-22 | 2015-10-27 | Closed | Won't Fix | v-dandl | Smoke |  |  | Yes | Valid
2644241 | CASH | Setup | 2 | 2015-10-28 | 2015-10-29 | Closed | Duplicate | v-xiasha | Test pass | TP2 |  | Yes
2644217 | CASH | Setup | 2 | 2015-10-28 | 2015-11-03 | Closed | Fixed | v-dandl | Test pass | TP2 |  | Yes | Valid
2632596 | People and Org Platform | UPA | 2 | 2015-10-22 | 2015-12-01 | Active |  | v-pengwu | Test pass | TP1 | Yes |  | Valid
2634700 | People and Org Platform | Mysite | 2 | 2015-10-23 | 2015-12-14 | Active |  | v-yiti | Test pass | TP1 | Yes |  | Valid
2644110 | WAC | Smoke | 2 | 2015-10-28 | 2016-02-19 | Closed | By Design | v-dandl | Smoke |  |  | Yes
2639650 | People and Org Platform | UPA | 3 | 2015-10-26 | 2015-12-01 | Active |  | v-pengwu | Test pass | TP1 | Yes |  | Valid
2639660 | People and Org Platform | Mysite |  | 2015-10-26 | 2015-12-01 | Active |  | v-yiti | Test pass | TP2 | Yes |  | Valid
2641231 | People and Org Platform | Mysite |  | 2015-10-27 | 2015-12-15 | Closed | Fixed | v-bitang | Test pass | TP2 | Yes |  | Valid
2649116 | CASH | Setup | 3 | 2015-10-30 | 2016-02-03 | Closed | Postponed | v-dandl | Test pass | TP2 |  | Yes | Valid
2655547 | OCW | Smoke |  | 2015-11-03 | 2015-11-06 | Closed | Won't Fix | v-bitang | Smoke |  |  | Yes | Valid
2318838 | SOX | Pre-install | 1 | 2015-06-04 | 2015-07-23 | Closed | External | v-dandl | Test pass | TP1 | Yes |  | Valid
2663307 | People and Org Platform | Mysite |  | 2015-11-06 | 2015-12-16 | Closed | Won't Fix | v-yiti | Test pass | TP2 |  | Yes
2900227 | OCW | Smoke | 3 | 2016-01-06 | 2016-01-08 | Active |  | v-dandl | Smoke |  |  | Yes | Valid
2627046 | CASH | Pre-install | 2 | 2015-10-20 | 2015-10-27 | Closed | External | v-dandl | Test pass | TP2 | Yes |  | Valid
2649135 | SPEED | Stsadmin |  | 2015-10-30 | 2015-11-13 | Closed | Not Repro | v-liach | Test pass | TP2 | Yes
2649352 | People and Org Platform | Mysite |  | 2015-10-30 | 2015-12-15 | Closed | Won't Fix | v-yiti | Test pass | TP2 | Yes
2649420 | People and Org Platform | UPA | 2 | 2015-10-30 | 2015-12-01 | Active |  | v-pengwu | Test pass | TP1 | Yes |  | Valid
2478232 | CASH | MinRole | 2 | 2015-08-11 | 2015-11-03 | Closed | Fixed | v-liach | Test pass | TP1 | Yes |  | Valid
2653337 | CASH | SKU |  | 2015-11-02 | 2016-02-03 | Closed | Postponed | v-chuya | Test pass | TP2 | Yes |  | Valid
2671033 | OCW | Smoke |  | 2015-11-11 | 2015-11-13 | Closed | Won't Fix | v-chuya | Smoke |  |  | Yes | Valid
2658467 | People and Org Platform | UPA |  | 2015-11-04 | 2015-11-06 | Closed | Fixed | v-liach | Test pass | TP1 | Yes |  | Valid
2658471 | People and Org Platform | UPA |  | 2015-11-04 | 2015-11-06 | Closed | Fixed | v-liach | Test pass | TP1 | Yes |  | Valid
2412176 | CASH | V2V | 2 | 2015-07-10 | 2015-08-17 | Closed | Not Repro | v-edyin | Test pass | TP1 | Yes
2658689 | People and Org Platform | Mysite |  | 2015-11-04 | 2015-11-16 | Closed | Fixed | v-bitang | Test pass | TP2 | Yes |  | Valid
2658700 | People and Org Platform | Mysite |  | 2015-11-04 | 2015-12-01 | Active |  | v-bitang | Test pass | TP2 | Yes |  | Valid
2658701 | People and Org Platform | Mysite |  | 2015-11-04 | 2016-01-12 | Closed | Fixed | v-bitang | Test pass | TP2 | Yes |  | Valid
2658702 | People and Org Platform | Mysite |  | 2015-11-04 | 2015-12-23 | Active |  | v-bitang | Test pass | TP2 | Yes |  | Valid
2658703 | People and Org Platform | Mysite |  | 2015-11-04 | 2015-12-01 | Active |  | v-bitang | Test pass | TP2 | Yes |  | Valid
2658705 | People and Org Platform | Mysite |  | 2015-11-04 | 2016-04-01 | Closed | Fixed | v-bitang | Test pass | TP2 | Yes |  | Valid
2658707 | People and Org Platform | Mysite |  | 2015-11-04 | 2015-12-01 | Active |  | v-bitang | Test pass | TP2 | Yes |  | Valid
2658708 | People and Org Platform | Mysite |  | 2015-11-04 | 2015-12-11 | Active |  | v-bitang | Test pass | TP2 | Yes |  | Valid
2658709 | People and Org Platform | Mysite |  | 2015-11-04 | 2015-12-01 | Active |  | v-bitang | Test pass | TP2 | Yes |  | Valid
2658710 | People and Org Platform | Mysite |  | 2015-11-04 | 2015-12-01 | Active |  | v-bitang | Test pass | TP2 | Yes |  | Valid
2658711 | People and Org Platform | Mysite |  | 2015-11-04 | 2015-12-01 | Active |  | v-bitang | Test pass | TP2 | Yes |  | Valid
2658715 | People and Org Platform | Mysite |  | 2015-11-04 | 2015-12-01 | Active |  | v-bitang | Test pass | TP2 | Yes |  | Valid
2672965 | CASH | Alternate Access Mappings |  | 2015-11-12 | 2015-11-25 | Closed | By Design | v-liach | Test pass | TP1 |  | Yes
2675116 | CASH | Alternate Access Mappings |  | 2015-11-13 | 2015-11-25 | Closed | Won't Fix | v-liach | Test pass | TP1 |  | Yes
2675443 | SPPPLAT | Smoke | 3 | 2015-11-13 | 2015-12-02 | Closed | Won't Fix | v-xiuye | Smoke |  |  | Yes | Valid
2678888 | Access | Smoke |  | 2015-11-16 | 2016-01-12 | Closed | Fixed | v-yiti | Smoke |  |  | Yes | Valid
2412195 | CASH | V2V | 2 | 2015-07-10 | 2015-08-17 | Closed | Not Repro | v-edyin | Test pass | TP1 | Yes
2697135 | OCW | Smoke | 3 | 2015-11-25 | 2016-02-25 | Closed | Won't Fix | v-bitang | Smoke |  |  | Yes | Valid
2685187 | CASH | IPU | 1 | 2015-11-19 | 2015-12-07 | Closed | Duplicate | v-yanb | Test pass | TP3 | Yes
2494891 | OCW | PRIME |  | 2015-08-19 | 2015-12-02 | Active |  | v-bitang | Test pass | TP1 | Yes |  | Valid
2697130 | OCW | Smoke | 3 | 2015-11-25 | 2016-02-25 | Closed | Won't Fix | v-liach | Smoke |  |  | Yes | Valid
2699419 | OCW | Smoke | 2 | 2015-11-27 | 2015-12-02 | Active |  | v-hanywa | Smoke |  |  | Yes | Valid
2699379 | People and Org Platform | UPA | 2 | 2015-11-27 | 2015-12-03 | Active |  | v-pengwu | Test pass | TP1 |  | Yes | Valid
2699385 | Excel Israel | Smoke | 3 | 2015-11-27 | 2016-02-28 | Closed | Fixed | v-dandl | Smoke |  |  | Yes | Valid
2701676 | OCW | Smoke | 3 | 2015-11-30 | 2015-12-04 | Closed | Won't Fix | v-chuya | Smoke |  |  | Yes | Valid
2701721 | OCW | Smoke | 3 | 2015-11-30 | 2016-03-21 | Closed | Not Repro | v-chuya | Smoke |  |  | Yes
2703488 | OCW | Smoke | 3 | 2015-12-01 | 2015-12-03 | Active |  | v-chuya | Smoke |  |  | Yes | Valid
2703595 | OCW | Smoke | 3 | 2015-12-01 | 2015-12-03 | Active |  | v-chuya | Smoke |  |  | Yes | Valid
2703592 | OCW | Smoke | 2 | 2015-12-01 | 2015-12-03 | Active |  | v-jinden | Smoke |  |  | Yes | Valid
2706413 | OCW | Smoke |  | 2015-12-02 | 2015-12-11 | Closed | Won't Fix | v-bitang | Smoke |  |  | Yes | Valid
2706237 | OCW | Smoke | 3 | 2015-12-02 | 2015-12-04 | Closed | Won't Fix | v-chuya | Smoke |  |  | Yes | Valid
2495191 | Office ecoSystem | Prime |  | 2015-08-19 | 2015-12-01 | Active |  | v-bitang | Test pass | TP1 | Yes |  | Valid
2706350 | SPPPLAT | Smoke | 2 | 2015-12-02 | 2015-12-04 | Active |  | v-chuya | Smoke |  |  | Yes | Valid
2721169 | Workplace Experiences | Smoke | 3 | 2015-12-04 | 2015-12-16 | Active |  | v-chuya | Smoke |  |  | Yes | Valid
2746466 | OCW | Smoke |  | 2015-12-07 | 2015-12-08 | Active |  | v-liach | Smoke |  |  | Yes | Valid
2746446 | OCW | Smoke | 2 | 2015-12-07 | 2015-12-08 | Active |  | v-yuljia | Smoke |  |  | Yes | Valid
2709806 | SPEED | WebApplication |  | 2015-12-03 | 2015-12-14 | Active |  | v-xiuye | Test pass | TP4 | Yes |  | Valid
2755466 | SPPPLAT | Smoke | 3 | 2015-12-08 | 2015-12-11 | Closed | Won't Fix | v-bitang | Smoke |  |  | Yes | Valid
2770567 | SOX | One off work | 2 | 2015-12-09 | 2015-12-16 | Closed | By Design | v-pengwu | One off work |  |  | Yes
2770602 | SOX | One off work | 2 | 2015-12-09 | 2015-12-16 | Closed | Not Repro | v-pengwu | One off work |  |  | Yes
2753688 | SPEED | IOS |  | 2015-12-08 | 2015-12-11 | Closed | Won't Fix | v-yiti | Test pass | TP2 | Yes
2771120 | Project | Smoke | 2 | 2015-12-09 | 2015-12-14 | Closed | Not Repro | v-yuljia | Smoke |  |  | Yes
2755503 | SPEED | IOS |  | 2015-12-08 | 2016-01-07 | Closed | Won't Fix | v-yiti | Test pass | TP2 | Yes
2770748 | Project | Smoke | 3 | 2015-12-09 | 2016-01-07 | Active |  | v-yuljia | Smoke |  |  | Yes | Valid
2780571 | SOX | Smoke | 3 | 2015-12-10 | 2015-12-30 | Closed | By Design | v-yawen | Smoke |  |  | Yes
2799341 | SOX | Smoke | 3 | 2015-12-11 | 2015-12-30 | Closed | Won't Fix | v-jinden | Smoke |  |  | Yes | Valid
2799239 | OCW | Smoke | 3 | 2015-12-11 | 2015-12-30 | Closed | By Design | v-hanywa | Smoke |  |  | Yes
2706404 | OCW | Smoke | 2 | 2015-12-02 | 2015-12-30 | Closed | By Design | v-chuya | Smoke |  | Yes
2851652 | OCW | Smoke | 2 | 2015-12-14 | 2016-02-25 | Closed | Won't Fix | v-yanb | Smoke |  |  | Yes | Valid
2851568 | SOX | Smoke | 3 | 2015-12-14 | 2015-12-18 | Closed | Won't Fix | v-yanb | Smoke |  |  | Yes | Valid
2799435 | CASH | IPU | 3 | 2015-12-11 | 2016-01-12 | Closed | Not Repro | v-xiasha | Test pass | TP1 | Yes
2849006 | CASH | Health | 3 | 2015-12-14 | 2015-12-21 | Closed | Won't Fix | v-xiuye | One off work |  | Yes |  | Valid
2851901 | OCW | Smoke | 2 | 2015-12-14 | 2016-02-25 | Closed | Won't Fix | v-yuljia | Smoke |  |  | Yes | Valid
2867326 | OCW | Smoke | 3 | 2015-12-15 | 2016-01-08 | Active |  | v-liach | Smoke |  |  | Yes | Valid
2877141 | Experiences | Smoke | 3 | 2015-12-16 | 2016-01-08 | Active |  | v-liach | Smoke |  |  | Yes | Valid
2852248 | People and Org Platform | Mysite | 2 | 2015-12-14 | 2016-01-21 | Closed | Fixed | v-bitang | Test pass | TP4 | Yes |  | Valid
2877302 | OCW | Smoke | 3 | 2015-12-16 | 2016-01-08 | Active |  | v-liach | Smoke |  |  | Yes | Valid
2877161 | OCW | Smoke | 3 | 2015-12-16 | 2016-01-08 | Active |  | v-yuljia | Smoke |  |  | Yes | Valid
2877162 | OCW | Smoke | 3 | 2015-12-16 | 2016-01-08 | Active |  | v-yuljia | Smoke |  |  | Yes | Valid
2879242 | OCW | Smoke | 2 | 2015-12-17 | 2016-01-08 | Active |  | v-liach | Smoke |  |  | Yes | Valid
2881125 | OCW | Smoke | 3 | 2015-12-18 | 2016-01-07 | Active |  | v-liach | Smoke |  |  | Yes | Valid
2885577 | OCW | Smoke | 3 | 2015-12-21 | 2016-01-07 | Active |  | v-yuljia | Smoke |  |  | Yes | Valid
2511950 | SOX | Backup & Restore | 3 | 2015-08-26 | 2015-09-22 | Closed | Won't Fix | v-dandl | Test pass | TP1 | Yes
2887162 | OCW | Smoke | 2 | 2015-12-22 | 2016-02-25 | Closed | Won't Fix | v-dandl | Smoke |  |  | Yes | Valid
2879290 | SOX | Stsadmin |  | 2015-12-17 | 2016-01-19 | Closed | By Design | v-bitang | Test pass | TP5 | Yes
2879350 | SPEED | Farm &configDB |  | 2015-12-17 | 2016-01-04 | Closed | By Design | v-xiuye | Test pass | TP5 | Yes
2880859 | People and Org Platform | Tiles | 2 | 2015-12-18 | 2016-02-25 | Active |  | v-pengwu | New feature |  | Yes |  | Valid
2880862 | SOX | Hybrid | 2 | 2015-12-18 | 2016-06-02 | Closed | By Design | v-pengwu | New feature |  | Yes
2888488 | OCW | Smoke | 3 | 2015-12-23 | 2016-02-25 | Closed | By Design | v-yuljia | Smoke |  |  | Yes
2885454 | SOX | Tiles | 2 | 2015-12-21 | 2016-02-04 | Active |  | v-pengwu | New feature |  | Yes |  | Valid
2888489 | OCW | Smoke | 3 | 2015-12-23 | 2016-02-25 | Closed | Won't Fix | v-yuljia | Smoke |  |  | Yes | Valid
2890151 | OCW | Smoke | 3 | 2015-12-24 | 2016-01-07 | Active |  | v-jinden | Smoke |  |  | Yes | Valid
2900330 | Workplace Experiences | Smoke | 2 | 2016-01-06 | 2016-02-25 | Active |  | v-yanb | Smoke |  |  | Yes | Valid
2892024 | OCW | Smoke | 2 | 2015-12-28 | 2016-01-07 | Closed | By Design | v-yanb | Smoke |  |  | Yes
2894008 | OCW | Smoke | 3 | 2015-12-30 | 2016-01-07 | Closed | Not Repro | v-hanywa | Smoke |  |  | Yes
2890880 | SOX | Tiles | 2 | 2015-12-25 | 2015-12-29 | Closed | By Design | v-pengwu | New feature |  | Yes
2892001 | OCW | Mysite | 3 | 2015-12-28 | 2016-01-21 | Closed | Not Repro | v-bitang | Test pass | TP5 | Yes |  |  |  | Yes
2894040 | OCW | Smoke | 3 | 2015-12-30 | 2016-01-08 | Active |  | v-jinden | Smoke |  |  | Yes | Valid
2893038 | MI6 | Usage Logging Framework | 3 | 2015-12-29 | 2016-01-07 | Closed | Won't Fix | v-xiuye | Test pass | TP5 | Yes |  | Valid
2893879 | OCW | Smoke | 3 | 2015-12-30 | 2016-01-07 | Active |  | v-yiti | Smoke |  |  | Yes | Valid
2894076 | OCW | Smoke | 2 | 2015-12-30 | 2016-01-09 | Active |  | v-bitang | Smoke |  |  | Yes | Valid
2895006 | OCW | Smoke | 3 | 2015-12-31 | 2016-01-08 | Active |  | v-yanb | Smoke |  |  | Yes | Valid
2894993 | CASH | Smoke | 3 | 2015-12-31 | 2016-01-08 | Active |  | v-jinden | Smoke |  |  | Yes | Valid
2895018 | OCW | Smoke | 3 | 2015-12-31 | 2016-01-07 | Active |  | v-yiti | Smoke |  |  | Yes | Valid
2895025 | OCW | Smoke | 2 | 2015-12-31 | 2016-02-25 | Active |  | v-xiuye | Smoke |  |  | Yes | Valid
2895019 | OCW | Smoke | 2 | 2015-12-31 | 2016-01-12 | Closed | Won't Fix | v-xiuye | Smoke |  |  | Yes | Valid
2902241 | Workplace Experiences | Smoke | 2 | 2016-01-07 | 2016-01-08 | Active |  | v-baoz | Smoke |  |  | Yes | Valid
2902261 | OCW | Smoke | 3 | 2016-01-07 | 2016-01-08 | Active |  | v-yuljia | Smoke |  |  | Yes | Valid
2902262 | SOX | Smoke | 2 | 2016-01-07 | 2016-01-11 | Closed | Not Repro | v-dandl | Smoke |  |  | Yes
2902447 | SOX | Smoke | 3 | 2016-01-07 | 2016-01-12 | Closed | By Design | v-yanb | Smoke |  |  | Yes
2893860 | CASH | Pre-install | 2 | 2015-12-30 | 2016-02-20 | Closed | Fixed | v-xiasha | Test pass | TP5 | Yes |  | Valid
2314040 | SOX | Pre-install | 2 | 2015-06-03 | 2015-07-17 | Closed | Not Repro | v-dandl | Test pass | TP1 | Yes
2908943 | OCW | Smoke | 3 | 2016-01-12 | 2016-02-25 | Closed | Won't Fix | v-baoz | Smoke |  |  | Yes | Valid
2909025 | OCW | Smoke | 1 | 2016-01-12 | 2016-02-29 | Closed | Not Repro | v-xiuye | Smoke |  |  | Yes
2909026 | OCW | Smoke | 3 | 2016-01-12 | 2016-01-25 | Closed | Won't Fix | v-hanywa | Smoke |  |  | Yes | Valid
2909043 | Workplace Experiences | Smoke | 3 | 2016-01-12 | 2016-01-15 | Active |  | v-yanb | Smoke |  |  | Yes | Valid
2909063 | SOX | Smoke | 1 | 2016-01-12 | 2016-01-13 | Closed | Duplicate | v-hanywa | Smoke |  |  | Yes
2910756 | People and Org Platform | Mysite | 3 | 2016-01-13 | 2016-01-14 | Closed | Won't Fix | v-bitang | Test pass | TP6 | Yes |  | Valid
2910841 | People and Org Platform | Mysite | 3 | 2016-01-13 | 2016-01-14 | Closed | Won't Fix | v-bitang | Test pass | TP6 | Yes |  | Valid
2413753 | CASH | V2V | 2 | 2015-07-10 | 2015-08-17 | Closed | Not Repro | v-edyin | Test pass | TP1 | Yes
2922497 | OCW | Smoke | 2 | 2016-01-20 | 2016-02-25 | Closed | Won't Fix | v-yiti | Smoke |  |  | Yes | Valid
2924308 | OCW | Smoke | 3 | 2016-01-21 | 2016-01-22 | Closed | Won't Fix | v-yanb | Smoke |  |  | Yes
2926245 | Experiences | Smoke | 2 | 2016-01-22 | 2016-01-25 | Active |  | v-baoz | Smoke |  |  | Yes | Valid
2926276 | OCW | Smoke | 3 | 2016-01-22 | 2016-02-25 | Closed | Won't Fix | v-hanywa | Smoke |  |  | Yes | Valid
2926304 | OCW | Smoke | 2 | 2016-01-22 | 2016-03-01 | Closed | Won't Fix | v-yanb | Smoke |  |  | Yes
2931544 | Project | Smoke | 3 | 2016-01-26 | 2016-01-27 | Active |  | v-jinden | Smoke |  |  | Yes | Valid
2933181 | Project | Smoke | 3 | 2016-01-27 | 2016-01-30 | Active |  | v-jinden | Smoke |  |  | Yes | Valid
2936164 | OCW | Mysite | 4 | 2016-01-28 | 2016-02-01 | Closed | Won't Fix | v-hanywa | Test pass | TP6 |  | Yes | Valid
2950897 | Access | Smoke | 2 | 2016-02-04 | 2016-02-25 | Closed | By Design | v-yawen | Smoke |  |  | Yes
2950899 | Access | Smoke | 2 | 2016-02-04 | 2016-02-22 | Closed | Fixed | v-yawen | Smoke |  |  | Yes | Valid
2964271 | SOX | Smoke | 1 | 2016-02-15 | 2016-02-16 | Closed | Fixed | v-yawen | Smoke |  |  | Yes | Valid
2968180 | Office International | Pre-install | 3 | 2016-02-18 | 2016-02-26 | Closed | Won't Fix | v-jinden | Test pass | TP7 |  | Yes | Valid
2973944 | SPEED | Web Application(shared Environment) | 2 | 2016-02-23 | 2016-03-14 | Closed | Not Repro | v-yanb | Test pass | TP7 | Yes
2974140 | SOX | MinRole | 2 | 2016-02-23 | 2016-02-25 | Closed | Duplicate | v-yanb | Test pass | TP7 | Yes
2983054 | Workplace Experiences | Devmain |  | 2016-02-29 | 2016-03-01 | Closed | Fixed | v-baoz | Devmain |  | Yes |  | Valid
2988675 | SPPPLAT | Central Admin |  | 2016-03-03 | 2016-03-11 | Active |  | v-hanywa | Test pass | TP8 | Yes |  | Valid
2990017 | SOX | Central Admin | 3 | 2016-03-04 | 2016-04-13 | Closed | Not Repro | v-hanywa | Test pass | TP8 | Yes
2993423 | People and Org Platform | Smoke | 2 | 2016-03-09 | 2016-03-07 | Closed | Fixed | v-dandl | Smoke |  | Yes |  | Valid
3000349 | Excel | Smoke | 3 | 2016-03-11 |  | Active |  | v-shijia | Smoke |  | Yes |  | Valid
2644438 | CASH | MinRole |  | 2015-10-28 | 2015-11-03 | Closed | Fixed | v-liach | Test pass | TP2 | Yes |  | Valid
3003924 | People and Org Platform | Mysite | 2 | 2016-03-14 | 2016-03-22 | Closed | Fixed | v-yiti | Test pass | TP8 | Yes |  | Valid
3007378 | SOX | setup | 4 | 2016-03-16 | 2016-10-12 | Closed | Won't Fix | v-baoz | Test pass | TP8 | Yes
3010678 | SOX | One off work | 3 | 2016-03-18 | 2016-03-18 | Active |  | v-yuljia | One off work |  |  | Yes | Valid
3017737 | Experiences | devmain | 1 | 2016-03-23 | 2016-03-28 | Active |  | v-dandl | Devmain |  | Yes |  | Valid
3017777 | Experiences | devmain | 2 | 2016-03-23 | 2016-04-22 | Closed | By Design | v-shijia | Devmain |  | Yes
3017778 | OCW | devmain | 2 | 2016-03-23 | 2016-04-29 | Closed | By Design | v-shijia | Devmain |  | Yes
3019515 | Project | Project Server | 2 | 2016-03-24 | 2016-04-21 | Closed | By Design | v-yuljia | Smoke |  | Yes
3019517 | Project | Project Server | 2 | 2016-03-24 | 2016-03-25 | Active |  | v-yuljia | Smoke |  | Yes |  | Valid
3019518 | OCW | devmain | 2 | 2016-03-24 | 2016-03-25 | Active |  | v-yuljia | Devmain |  |  | Yes | Valid
3019524 | Project | devmain | 2 | 2016-03-24 | 2016-03-25 | Active |  | v-yuljia | Devmain |  | Yes |  | Valid
3021077 | OCW | Smoke | 3 | 2016-03-25 | 2016-03-28 | Active |  | v-yiti | Smoke |  |  | Yes | Valid
3029922 | OCW | Smoke | 2 | 2016-04-01 | 2016-04-05 | Active |  | v-yawen | Smoke |  |  | Yes | Valid
3033662 | SOX | Smoke | 2 | 2016-04-05 | 2016-04-07 | Closed | Not Repro | v-shijia | Smoke |  |  | Yes
3033668 | SOX | DLP | 1 | 2016-04-05 | 2016-04-08 | Closed | Not Repro | v-dandl | PU verify | April PU | Yes |  |  |  | Yes
3042700 | SOX | Smoke | 2 | 2016-04-12 | 2016-04-12 | Active |  | v-shijia | Test pass | TP9 |  | Yes | Valid
3042701 | SOX | Smoke | 3 | 2016-04-12 | 2016-04-13 | Active |  | v-shijia | Test pass | TP9 |  | Yes | Valid
3044757 | SOX | Smoke | 3 | 2016-04-13 | 2016-04-14 | Active |  | v-jinden | Smoke |  |  | Yes | Valid
3046210 | OCW | Smoke | 3 | 2016-04-14 | 2016-05-30 | Active |  | v-yawen | Smoke |  |  | Yes | Valid
3046235 | SOX | Smoke | 3 | 2016-04-14 | 2016-04-15 | Active |  | v-yawen | Smoke |  |  | Yes | Valid
3047308 | SOX | SKU | 3 | 2016-04-15 | 2016-09-29 | Closed | Won't Fix | v-shijia | Test pass | TP9 | Yes
3050032 |  | Hybrid Taxonomy | 2 | 2016-04-18 | 2016-04-29 | Closed | Won't Fix | v-yuljia | New feature |  | Yes
3052917 | SOX | Smoke | 1 | 2016-04-20 | 2016-04-21 | Closed | Fixed | v-dandl | Smoke |  | Yes |  | Valid
3054407 | SOX | MinRole | 2 | 2016-04-21 | 2016-05-26 | Active |  | v-xiuye | PU verify | May PU | Yes |  | Valid
3054428 |  | Hybrid Taxonomy | 2 | 2016-04-21 | 2016-04-29 | Closed | Won't Fix | v-yuljia | New feature |  |  | Yes
3056952 | SOX | Backup & Restore | 2 | 2016-04-22 | 2016-05-09 | Closed | Won't Fix | v-baoz | PU verify | May PU |  | Yes
3065280 | SOX | Smoke | 3 | 2016-04-29 | 2016-04-29 | Active |  | v-xiasha | Smoke |  |  | Yes | Valid
3073903 | SPPPLAT | Smoke | 3 | 2016-05-06 | 2016-06-02 | Active |  | v-bitang | Smoke |  | Yes |  | Valid
3076231 | OCW | Smoke | 3 | 2016-05-09 | 2016-05-11 | Active |  | v-shijia | Smoke |  |  | Yes | Valid
3082168 | SOX | devmain | 1 | 2016-05-13 | 2016-05-13 | Active |  | v-dandl | Devmain |  |  | Yes | Valid
3082171 | SOX | devmain | 2 | 2016-05-13 | 2016-05-13 | Active |  | v-shijia | Devmain |  | Yes |  | Valid
3082172 | SOX | devmain | 3 | 2016-05-13 | 2016-05-13 | Active |  | v-shijia | Devmain |  | Yes |  | Valid
3082176 | SOX | devmain | 3 | 2016-05-13 | 2016-05-13 | Active |  | v-shijia | Devmain |  | Yes |  | Valid
3082178 | SOX | devmain | 3 | 2016-05-13 | 2016-05-13 | Active |  | v-shijia | Devmain |  | Yes |  | Valid
3082187 | SOX | devmain | 2 | 2016-05-13 | 2016-05-13 | Active |  | v-shijia | Devmain |  | Yes |  | Valid
3082196 | SOX | devmain | 2 | 2016-05-13 | 2016-05-13 | Active |  | v-shijia | Devmain |  | Yes |  | Valid
3088801 | SOX | SKU | 3 | 2016-05-19 | 2016-09-18 | Closed | Duplicate | v-jinden | Test pass | TP10 | Yes
3090163 | CASH | MinRole | 2 | 2016-05-20 | 2016-07-26 | Closed | Not Repro | v-xiuye | PU verify | June PU | Yes
3090246 | SOX | Smoke | 3 | 2016-05-20 | 2016-05-20 | Active |  | v-wenxxu | Smoke |  |  | Yes | Valid
2511959 | SOX | Backup & Restore | 3 | 2015-08-26 | 2015-09-22 | Closed | Won't Fix | v-dandl | Test pass | TP1 | Yes
2426642 | CASH | V2V | 1 | 2015-07-17 | 2015-08-17 | Closed | Not Repro | v-pengwu | Test pass | TP1 | Yes
3109528 | SOX | Smoke | 3 | 2016-06-08 | 2016-06-08 | Active |  | v-zifen | Smoke |  |  | Yes | Valid
3113962 | SOX | Smoke | 3 | 2016-06-12 | 2016-06-12 | Active |  | v-wenxxu | Smoke |  |  | Yes | Valid
3113963 | SOX | Smoke | 2 | 2016-06-12 | 2016-06-12 | Active |  | v-shijia | Smoke |  |  | Yes | Valid
3114095 | SOX | Smoke | 3 | 2016-06-13 | 2016-06-13 | Active |  | v-zifen | Smoke |  |  | Yes | Valid
3114124 | SOX | Smoke | 3 | 2016-06-13 | 2016-06-13 | Active |  | v-shijia | Smoke |  |  | Yes | Valid
3115455 | OCW | Smoke | 3 | 2016-07-26 | 2016-07-26 | Closed | Duplicate | v-shijia | Test pass | TP11 |  | Yes
2426679 | CASH | V2V | 1 | 2015-07-17 | 2015-08-28 | Closed | Duplicate | v-pengwu | Test pass | TP1 | Yes
3130245 | Onprem | Backup & Restore | 2 | 2016-06-27 | 2016-12-09 | Closed | Fixed | v-dandl | PU verify | July PU | Yes |  | Valid
3132718 | SOX | Smoke | 3 | 2016-06-29 | 2016-06-29 | Active |  | v-yuljia | Smoke |  |  | Yes | Valid
3132889 | SOX | setup | 3 | 2016-06-29 | 2016-06-29 | Closed |  | v-zifen | Test pass | TP12 |  | Yes
3132916 | SOX | Devmain | 2 | 2016-06-29 | 2016-06-29 | Active |  | v-pakang | Devmain |  |  | Yes | Valid
3133997 | Storage, Networking and Performance | BCS | 3 | 2016-06-30 |  | Active |  | v-shijia | Test pass | TP12 |  | Yes | Valid
3134003 | CASH | setup | 3 | 2016-06-30 | 2016-07-26 | Closed | Won't Fix | v-shijia | Test pass | TP12 |  | Yes | Valid
3134008 | SOX | Onprem | 3 | 2016-06-30 | 2016-11-03 | Closed | Fixed | v-shijia | Test pass | TP12 |  | Yes | Valid
3134017 | CASH | setup | 3 | 2016-06-30 |  | Active |  | v-yuljia | Test pass | TP12 |  | Yes | Valid
3134018 | SPEED | Web Application | 3 | 2016-06-30 |  | Active |  | v-yuljia | Test pass | TP12 |  | Yes | Valid
2868444 | Search and Graph | Smoke | 3 | 2015-12-15 | 2016-01-12 | Closed | By Design | v-yanb | Smoke |  | Yes
2696730 | SPPPLAT | V2V |  | 2015-11-25 | 2015-12-25 | Closed | Won't Fix | v-xiasha | Test pass | TP2 |  | Yes | Valid
3134027 | SOX | Smoke | 3 | 2016-06-30 |  | Active |  | v-shijia | Smoke |  |  | Yes | Valid
3134053 | CASH | setup | 3 | 2016-06-30 | 2016-07-26 | Closed | Won't Fix | v-shijia | Test pass | TP12 | Yes |  | Valid
3134055 | People and Org Platform | Smoke | 3 | 2016-06-30 | 2016-07-01 | Closed | By Design | v-yawen | Smoke |  |  | Yes
3144996 | SOX | MinRole | 3 | 2016-07-12 | 2016-07-12 | Active |  | v-dandl | Test pass | TP12 | Yes |  | Valid
3146364 | SOX | Hybrid | 2 | 2016-07-13 | 2016-07-13 | Active |  | v-pengwu | New feature |  | Yes |  | Valid
3147450 | SOX | Hybrid | 2 | 2016-07-14 | 2016-07-14 | Active |  | v-pengwu | New feature |  | Yes |  | Valid
3148809 | SOX | Hybrid | 2 | 2016-07-15 | 2016-08-01 | Closed | Fixed | v-yuljia | New feature |  |  | Yes | Valid
3151037 | SP SOXHybrid | HybridAppLauncher2013 | 2 | 2016-05-06 | 2016-05-10 | Closed | Not Repro | v-pengwu | New feature |  | Yes
3151037 | SOX | Hybrid | 2 | 2016-07-17 | 2016-08-02 | Closed | Fixed | v-pengwu | New feature |  | Yes |  | Valid
3153645 | SOX | Hybrid | 2 | 2016-07-20 | 2016-08-01 | Closed | Fixed | v-pengwu | New feature |  | Yes |  | Valid
3156131 | SOX | Hybrid | 2 | 2016-07-22 | 2016-08-02 | Closed | Fixed | v-yuljia | New feature |  |  | Yes | Valid
3157822 | Storage, Networking and Performance | BCS | 1 | 2016-07-24 | 2016-08-01 | Closed | Fixed | v-jinden | PU verify | August PU | Yes |  | Valid
3158818 | SOX | Managed Account | 3 | 2016-07-26 | 2016-07-26 | Active |  | v-dandl | PU verify | August PU | Yes |  | Valid
3164723 | SOX | Hybrid | 2 | 2016-08-02 | 2016-08-07 | Closed | Fixed | v-pengwu | New feature |  |  | Yes | Valid
3165636 | SOX | Hybrid | 2 | 2016-08-02 | 2016-08-07 | Closed | Won't Fix | v-pengwu | New feature |  |  | Yes | Valid
3171596 | CASH | setup | 3 | 2016-08-10 | 2016-08-11 | Closed | Duplicate | v-zifen | Test pass | TP13 |  | Yes
3174343 | SOX | Bug Bash |  | 2016-08-12 | 2016-09-18 | Closed | By Design | v-yawen | Bug Bash |  |  | Yes
3174346 | SOX | Bug Bash | 1 | 2016-08-12 | 2016-10-28 | Closed | Fixed | v-baoz | Bug Bash |  |  | Yes | Valid
3174350 | SOX | Bug Bash | 3 | 2016-08-12 | 2016-09-18 | Closed | By Design | v-yawen | Bug Bash |  |  | Yes
3174356 | SOX | Bug Bash | 2 | 2016-08-12 | 2016-08-31 | Closed | Duplicate | v-baoz | Bug Bash |  |  | Yes
3174359 | SOX | Bug Bash | 2 | 2016-08-12 | 2016-09-06 | Closed | By Design | v-hanywa | Bug Bash |  |  | Yes
3174362 | SOX | Bug Bash | 1 | 2016-08-12 | 2016-08-30 | Closed | Duplicate | v-baoz | Bug Bash |  |  | Yes
3178137 | SOX | SKU | 2 | 2016-08-17 | 2016-08-17 | Closed | Duplicate | v-doshen | Test pass | TP13 | Yes
3185318 | SOX | RBS | 2 | 2016-08-24 | 2016-08-29 | Closed | Not Repro | v-baoz | PU verify | Sep PU | Yes
3185353 | SOX | Hybrid |  | 2016-08-24 | 2016-10-27 | Closed | By Design | v-pengwu | New feature |  |  | Yes
3185358 | SOX | Hybrid |  | 2016-08-24 | 2016-08-29 | Closed | Fixed | v-pengwu | New feature |  |  | Yes | Valid
3188579 | SOX | RBS | 3 | 2016-08-26 | 2016-08-29 | Closed | Won't Fix | v-baoz | PU verify | September PU |  | Yes | Valid
3190868 | SOX | SKU | 2 | 2016-08-29 | 2016-08-29 | Closed | Duplicate | v-doshen | PU verify | September PU | Yes
2644334 | WAC | Smoke | 2 | 2015-10-28 | 2016-02-19 | Closed | By Design | v-dandl | Smoke |  | Yes
3194963 | Experiences | Smoke | 2 | 2016-09-02 | 2016-10-12 | Closed | Not Repro | v-baoz | Smoke |  | Yes
3205266 | SOX | Bug Bash |  | 2016-09-13 | 2016-09-13 | Closed | Fixed | v-zifen | Bug Bash |  |  | Yes | Valid
3211593 | SOX | Central Admin |  | 2016-09-19 | 2016-12-09 | Closed | Fixed | v-zifen | Test pass | TP14 | Yes |  | Valid
3220891 | SOX | Hybrid |  | 2016-09-28 | 2016-10-12 | Closed | Fixed | v-baoz | New feature |  |  | Yes | Valid
3222229 | ODWeb | Smoke | 2 | 2016-09-29 | 2016-10-21 | Closed | Duplicate | v-jinden | Smoke |  | Yes
3234237 | SOX | SKU | 3 | 2016-10-11 | 2016-10-12 | Closed | Won't Fix | v-doshen | Test pass | TP15 | Yes
3234248 | SOX | Hybrid |  | 2016-10-11 | 2016-10-11 | Active |  | v-baoz | New feature |  | Yes |  | Valid
3234251 | SOX | Hybrid |  | 2016-10-11 | 2016-11-02 | Resolved | Fixed | v-baoz | New feature |  | Yes |  | Valid
3234255 | SOX | Hybrid |  | 2016-10-11 | 2016-10-13 | Closed | Fixed | v-baoz | New feature |  | Yes |  | Valid
3234273 | OCW | Smoke | 3 | 2016-10-11 | 2016-10-11 | Active |  | v-jinden | Smoke |  |  | Yes | Valid
3236238 | SOX | Custom Tiles |  | 2016-10-12 | 2016-12-09 | Closed |  | v-zifen | Test pass | TP15 | Yes
3517771 | SP SOXHybrid | HybridAppLauncher2013 | 3 | 2016-04-01 | 2016-04-12 | Closed | Fixed | zhigzh | New feature |  | Yes |  | Valid
3517893 | SP SOXHybrid | HybridAppLauncher2013 | 2 | 2016-04-07 | 2016-04-13 | Closed | Fixed | v-pengwu | New feature |  | Yes |  | Valid
3517938 | SP SOXHybrid | HybridAppLauncher2013 | 2 | 2016-04-11 | 2016-05-09 | Closed | Not Repro | v-pengwu | New feature |  | Yes
3517981 | SP SOXHybrid | HybridAppLauncher2013 | 3 | 2016-04-13 | 2016-04-15 | Closed | Fixed | v-pengwu | New feature |  |  | Yes | Valid
3520185 | SP SOXHybrid | HybridAppLauncher2013 | 3 | 2016-04-15 | 2016-04-20 | Closed | Fixed | v-pengwu | New feature |  |  | Yes | Valid
3521494 | SP SOXHybrid | HybridAppLauncher2013 | 3 | 2016-04-15 | 2016-05-30 | Closed | Fixed | v-pengwu | New feature |  | Yes |  | Valid
3526304 | SP SOXHybrid | HybridAppLauncher2013 | 3 | 2016-04-20 | 2016-04-29 | Closed | Fixed | v-pengwu | New feature |  |  | Yes | Valid
3526306 | SP SOXHybrid | HybridAppLauncher2013 | 3 | 2016-04-20 | 2016-05-27 | Closed | Fixed | v-pengwu | New feature |  |  | Yes | Valid
3526308 | SP SOXHybrid | HybridAppLauncher2013 | 2 | 2016-04-20 | 2016-05-10 | Closed | Not Repro | v-pengwu | New feature |  | Yes
3603320 | SP SOXHybrid | HybridAppLauncher2013 | 2 | 2016-04-25 | 2016-04-29 | Closed | Fixed | v-pengwu | New feature |  | Yes |  | Valid
3628411 | SP SOXHybrid | HybridAppLauncher2013 | 3 | 2016-04-28 | 2016-04-29 | Closed | By Design | v-pengwu | New feature |  |  | Yes
3628531 | SP SOXHybrid | HybridAppLauncher2013 | 2 | 2016-05-05 | 2016-05-13 | Resolved | Fixed | lju | New feature |  |  | Yes | Valid
3628550 | SP SOXHybrid | HybridAppLauncher2013 | 2 | 2016-05-06 | 2016-05-09 | Closed | External | v-pengwu | New feature |  |  | Yes | Valid
3628822 | SP SOXHybrid | HybridAppLauncher2013 | 3 | 2016-05-25 | 2016-06-09 | Closed | Fixed | v-pengwu | New feature |  |  | Yes | Valid
2632164 | Access | Smoke | 2 | 2015-10-22 | 2016-02-26 | Closed | Fixed | v-dandl | Smoke |  | Yes |  | Valid
3629288 | SP SOXHybrid | HybridAppLauncher2013 | 3 | 2016-06-24 | 2016-06-24 | Active |  | v-pengwu | New feature |  |  | Yes | Valid
3261976 | Search and Graph | Smoke | 2 | 2016-11-03 | 2016-12-02 | Closed | External | v-jinden | Smoke |  | Yes |  | Valid
3262039 | SOX | Smoke | 2 | 2016-11-03 | 2016-12-02 | Closed | Not Repro | v-chekal | Smoke |  |  | Yes
3265000 | SOX | SCOM | 2 | 2016-11-07 | 2016-11-17 | Closed | Not Repro | v-jinden | Test pass | TP16 | Yes
3271074 | SOX | MinRole |  | 2016-11-14 | 2016-11-17 | Closed | Fixed | v-zhaxue | Test pass | TP17 | Yes |  | Valid
3279255 | SOX | Setup |  | 2016-11-23 | 2016-11-23 | Active |  | v-zifen | PU verify | December PU |  | Yes | Valid
3137789 | SOX | Setup |  | 2016-07-04 | 2016-12-07 | Closed | Won't Fix | v-zifen | Test pass | TP12
3291732 | SOX | MinRole |  | 2016-12-08 | 2016-12-08 | Active |  | v-zhaxue | Test pass | TP18 | Yes |  | Valid

## Communication
Time | Average Microsoft Fulltime employee request response within x hours | Communication to Microsoft with test Plan, test owner, test schedule | Technical issues were resolved by date agreed upon by Microsoft and supplier
Per week | Target 2 hours | Yes/No | Yes/No
2016-10-10 | 30 Min | Yes | Yes
2016-10-17 | 20 Min | Yes | Yes
2016-10-24 | 20 Min | Yes | Yes
2016-10-31 | 20 Min | Yes | Yes
2016-11-07 | 20 Min | Yes | Yes
2016-11-14 | 20 Min | Yes | Yes
2016-11-21 | 20 Min | Yes | Yes
2016-11-28 | 20 Min | Yes | Yes

## Resource
Name | Alias | Onboard Date | Title | Skillset | Ramp up time | Attrition | Comments | Level | Skill
Yanping Wen | v-yawen | 2015-12-07 | SDET Lead | Lead |  | Yes/No |  | 1 | Test cases execution
Dandan Liu | v-dandl | 2015-04-27 | SDET3 | 3 |  |  |  | 1 | Test cases maintain
Xiujuan Ye | v-xiuye | 2015-07-17 | SDET2 | 2 |  |  |  | 1 | Bug regression
Baoli Zhang | v-baoz | 2015-07-08 | SDET2 | 2 |  |  |  | 1 | C#
Yingchun Tian | v-yiti | 2015-11-03 | SDET1 | 1 |  |  |  | 1 | PowerShell Script
Yuling Jiao | v-yuljia | 2015-08-03 | SDET1 | 1 |  |  |  | 2 | Own main features
Jing Deng | v-jinden | 2015-10-12 | SDET1 | 1 |  |  |  | 2 | Mentor for new resource
Zian Feng | v-zifen | 2016-05-23 | SDET1 | 1 |  |  |  | 3 | Technial support
Dongming Shen | v-doshen | 2016-02-18 | SDET1 | 2 |  |  |  | 3 | QA related trouble shooting
Kalyana Sudha Cherukuri | v-chekal | 2016-09-20 | SDET1 | 1 |  |  |  | 3 | Own automation test
Pengfei Yan | v-pengy | 2016-11-14 | PM1 | PM1 |  |  |  | Lead | Delivery quality insurance
Xue Zhang | v-zhaxue | 2016-07-01 | SDET1 | 1 |  |  |  | Lead | Project management
Xue Huang | v-xueh | 2016-11-01 | SDET1 | 1 |  |  |  | Lead | Resource management
Chao Cui | v-chacui | 2016-04-05 | SDET1 | 1 |  |  |  | Lead | Client expectation management
Bin Yan | v-yanb | 2015-11-01 | SDET1 | 1 |  |  |  | PM1 | Photoshop

## Resource&Tasks
Tasks | Person
UI Design | 1
Power BI | 3
Smoke | 1
ad Hoc | 1
Regression | 9
If we just count for billable persion?

## Efficency Improvement
Save Test hours per test pass | Extra work doing
8 | 16 | Backup Restore UI automation.